## Summary Dashboard
BAAGICHA FEATURE TRACKER — EXECUTIVE SUMMARY
Backend (Laravel) |  |  | Mobile (React Native)
Metric | Count | Status | Metric | Count | Status
Total Migrations | 91 | Done | Total Screens | 42 | Done
Total Models | 83 | Done | Total Components | 40 | Done
Total API Routes | 140 | Done | Total Navigation Stacks | 6 | Done
Total Controllers | 109 | Done | Total API Services | 18 | Done
Total Services | 24 | Done | Total Stores | 6 | Done
Total Form Requests | 33 | Done | Total Hooks | 20 | Done
Total API Resources | 15 | Done | Total Native Modules | 13 | Done
Total Jobs | 6 | Done | Pending Items | 3 | Pending
Total Policies | 9 | Done | In Progress Items | 3 | In Progress
Total Admin Views | 120 | Done
PENDING / IN-PROGRESS ITEMS (Action Required)
Project | Item | Description | Status
Mobile | MyFarmSegment.tsx | My Farm dashboard uses hard-coded mock data. Needs real API integration in Phase 6 | In Progress
Mobile | FeedDetailScreen.tsx | Comments are mocked, no live comment loading | In Progress
Mobile | DiscoverScreen.tsx | Top half is mock dashboard (Do Now, weather, tasks, alerts). Needs real API data | In Progress
Mobile | ToolsScreen.tsx + 26 widgets | Kisan Tools UI catalog complete. All 26 calculator widgets show 'Coming soon' | Pending
Mobile | UserProfileScreen.tsx | Follow/Connect buttons show 'coming soon' toast — backend integration pending | Pending
Backend | WeatherEngine.php | Minor TODO: integrate fertilizer activity log (daysSinceLastFertilization hard-coded to 999) | In Progress
Backend | CartService.php | Minor TODO: Validate coupon via CouponService in Phase 5 | In Progress

## Backend (Laravel)
S.No | Module / Feature | Sub-Module | Item Type | Item Name / File | Description | Status | Notes / TODOs
Auth (Sanctum + Social)
1 | Auth (Sanctum + Social) | Database | Migration | alter_users_table_for_social_auth | Adds social auth fields to users table | Done
2 | Auth (Sanctum + Social) | Database | Migration | phone_verifications | OTP verification tracking table | Done
3 | Auth (Sanctum + Social) | Database | Migration | social_accounts | Linked social provider accounts | Done
4 | Auth (Sanctum + Social) | Database | Migration | personal_access_tokens (Sanctum) | API token table | Done
5 | Auth (Sanctum + Social) | Database | Migration | device_tokens | FCM device token storage | Done
Auth (Sanctum + Social)
6 | Auth (Sanctum + Social) | Models | Model | User | Core user with soft deletes, social auth traits | Done
7 | Auth (Sanctum + Social) | Models | Model | PhoneVerification | OTP state tracking | Done
8 | Auth (Sanctum + Social) | Models | Model | SocialAccount | OAuth provider linkage | Done
9 | Auth (Sanctum + Social) | Models | Model | DeviceToken | Push notification tokens | Done
Auth (Sanctum + Social)
10 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/register | Email registration | Done
11 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/login | Email/phone login | Done
12 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/otp/send | Send phone OTP | Done
13 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/otp/verify | Verify phone OTP | Done
14 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/social | Google/Facebook OAuth login | Done
15 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/forgot-password | Password reset link | Done
16 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/reset-password | Reset password | Done
17 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/logout | Logout current session | Done
18 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/logout-all | Logout all devices | Done
19 | Auth (Sanctum + Social) | API Routes | API Route | GET /api/v1/auth/profile | Get authenticated user profile | Done
20 | Auth (Sanctum + Social) | API Routes | API Route | PUT /api/v1/auth/profile | Update profile | Done
21 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/refresh | Refresh Sanctum token | Done
22 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/change-password | Change password | Done
23 | Auth (Sanctum + Social) | API Routes | API Route | GET /api/v1/auth/email/status | Email verification status | Done
24 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/auth/email/resend | Resend verification email | Done
25 | Auth (Sanctum + Social) | API Routes | API Route | GET /api/v1/auth/email/verify/{id}/{hash} | Verify email link | Done
26 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/devices/register | Register FCM device token | Done
27 | Auth (Sanctum + Social) | API Routes | API Route | DELETE /api/v1/devices/unregister | Unregister device token | Done
28 | Auth (Sanctum + Social) | API Routes | API Route | POST /api/v1/devices/link | Link orphan device tokens | Done
Auth (Sanctum + Social)
29 | Auth (Sanctum + Social) | Controllers | Controller | Api/AuthController | Logout, profile, refresh, change password | Done
30 | Auth (Sanctum + Social) | Controllers | Controller | Api/Auth/EmailAuthController | Register, login | Done
31 | Auth (Sanctum + Social) | Controllers | Controller | Api/Auth/EmailVerificationController | Email verify/resend/status | Done
32 | Auth (Sanctum + Social) | Controllers | Controller | Api/Auth/PasswordResetController | Forgot/reset password | Done
33 | Auth (Sanctum + Social) | Controllers | Controller | Api/Auth/PhoneAuthController | OTP send/verify | Done
34 | Auth (Sanctum + Social) | Controllers | Controller | Api/Auth/SocialAuthController | Social OAuth handler | Done
35 | Auth (Sanctum + Social) | Controllers | Controller | Api/DeviceTokenController | Device token CRUD | Done
36 | Auth (Sanctum + Social) | Controllers | Controller | Auth/* (Web) | Laravel Breeze web auth scaffolding | Done
Auth (Sanctum + Social)
37 | Auth (Sanctum + Social) | Services | Service | Auth/EmailAuthService | Email registration/login logic | Done
38 | Auth (Sanctum + Social) | Services | Service | Auth/PhoneAuthService | OTP generation & verification logic | Done
39 | Auth (Sanctum + Social) | Services | Service | Auth/ProfileService | Profile updates & password changes | Done
40 | Auth (Sanctum + Social) | Services | Service | SmsService | SMS gateway abstraction | Done
Auth (Sanctum + Social)
41 | Auth (Sanctum + Social) | Form Requests | Form Request | Auth/RegisterRequest | Registration validation rules | Done
42 | Auth (Sanctum + Social) | Form Requests | Form Request | Auth/LoginRequest | Login validation rules | Done
43 | Auth (Sanctum + Social) | Form Requests | Form Request | Auth/SendOtpRequest | Phone OTP send validation | Done
44 | Auth (Sanctum + Social) | Form Requests | Form Request | Auth/VerifyOtpRequest | OTP verify validation | Done
45 | Auth (Sanctum + Social) | Form Requests | Form Request | Auth/ChangePasswordRequest | Change password validation | Done
46 | Auth (Sanctum + Social) | Form Requests | Form Request | Auth/UpdateProfileRequest | Profile update validation | Done
Auth (Sanctum + Social)
47 | Auth (Sanctum + Social) | Middleware | Middleware | DetectMobileAppRedirect | Redirect mobile browsers to app download | Done
48 | Auth (Sanctum + Social) | Middleware | Middleware | SecurityHeaders | Security response headers | Done
49 | Auth (Sanctum + Social) | Middleware | Middleware | RedirectIfNotAdmin | Admin role gate | Done
50 | Auth (Sanctum + Social) | Middleware | Middleware | CacheResponse | Page-level HTTP caching | Done
User Profiles & Preferences
51 | User Profiles & Preferences | Database | Migration | user_profiles | Extended user profile data | Done
52 | User Profiles & Preferences | Database | Migration | user_preferences | User settings (language, units, notifications) | Done
53 | User Profiles & Preferences | Database | Migration | user_orchards | User orchard ownership | Done
54 | User Profiles & Preferences | Database | Migration | orchard_varieties | Varieties planted in each orchard | Done
55 | User Profiles & Preferences | Database | Migration | orchard_activities | Orchard diary/activity log | Done
56 | User Profiles & Preferences | Database | Migration | orchard_blocks | Sub-divisions within orchards | Done
57 | User Profiles & Preferences | Database | Migration | orchard_rootstocks | Rootstock mapping per orchard | Done
58 | User Profiles & Preferences | Database | Migration | orchard_block_varieties | Variety-rootstock-block linkage | Done
59 | User Profiles & Preferences | Database | Migration | add_notification_location_flags_to_user_preferences | Location/notification preference flags | Done
User Profiles & Preferences
60 | User Profiles & Preferences | Models | Model | UserProfile | Extended profile (village, district, state, etc.) | Done
61 | User Profiles & Preferences | Models | Model | UserPreference | Settings & notification toggles | Done
62 | User Profiles & Preferences | Models | Model | UserOrchard | Orchard ownership & metadata | Done
63 | User Profiles & Preferences | Models | Model | OrchardVariety | Variety planted in orchard | Done
64 | User Profiles & Preferences | Models | Model | OrchardActivity | Diary entry for orchard work | Done
65 | User Profiles & Preferences | Models | Model | OrchardBlock | Geographic/physical block in orchard | Done
66 | User Profiles & Preferences | Models | Model | OrchardBlockVariety | Block-level variety mapping | Done
User Profiles & Preferences
67 | User Profiles & Preferences | API Routes | API Route | GET/POST/PUT/DELETE /api/v1/orchards | Orchard CRUD | Done
68 | User Profiles & Preferences | API Routes | API Route | GET/POST/PUT/DELETE /api/v1/orchards/{orchard}/varieties | Orchard variety CRUD | Done
69 | User Profiles & Preferences | API Routes | API Route | GET/POST/PUT/DELETE /api/v1/orchards/{orchard}/blocks | Orchard block CRUD | Done
70 | User Profiles & Preferences | API Routes | API Route | GET/POST/PUT/DELETE /api/v1/orchard-activities | Activity diary CRUD | Done
71 | User Profiles & Preferences | API Routes | API Route | GET/POST /api/v1/orchards/{orchard}/spray-logs | Spray log list/create | Done
72 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/spray-logs/{log} | Spray log detail | Done
73 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/users/suggested | Suggested friends list | Done
74 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/users/me/stats | Own stats (posts, likes, etc.) | Done
75 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/users/me/posts | Own posts feed | Done
76 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/users/me/liked-posts | Liked posts feed | Done
77 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/users/me/activities | Own activity feed | Done
78 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/users/{user} | Public user profile | Done
79 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/locations/states | List Indian states | Done
80 | User Profiles & Preferences | API Routes | API Route | GET /api/v1/locations/districts | List districts by state | Done
User Profiles & Preferences
81 | User Profiles & Preferences | Controllers | Controller | Api/UserController | Suggested users, public profile, stats | Done
82 | User Profiles & Preferences | Controllers | Controller | Api/UserOrchardController | Orchard CRUD | Done
83 | User Profiles & Preferences | Controllers | Controller | Api/OrchardVarietyController | Orchard variety CRUD | Done
84 | User Profiles & Preferences | Controllers | Controller | Api/OrchardBlockController | Orchard block CRUD | Done
85 | User Profiles & Preferences | Controllers | Controller | Api/OrchardActivityController | Activity diary CRUD | Done
86 | User Profiles & Preferences | Controllers | Controller | Api/SprayLogController | Spray log management | Done
87 | User Profiles & Preferences | Controllers | Controller | Api/LocationController | States & districts | Done
88 | User Profiles & Preferences | Controllers | Controller | ProfileController | Web profile management | Done
89 | User Profiles & Preferences | Controllers | Controller | PreferenceController | Web preferences | Done
User Profiles & Preferences
90 | User Profiles & Preferences | Services | Service | Profile/DashboardService | User dashboard data aggregation | Done
91 | User Profiles & Preferences | Services | Service | SprayScheduleService | Spray calendar & task logic | Done
User Profiles & Preferences
92 | User Profiles & Preferences | Form Requests | Form Request | StoreOrchardRequest | Create orchard validation | Done
93 | User Profiles & Preferences | Form Requests | Form Request | UpdateOrchardRequest | Update orchard validation | Done
94 | User Profiles & Preferences | Form Requests | Form Request | StoreOrchardBlockRequest | Create block validation | Done
95 | User Profiles & Preferences | Form Requests | Form Request | UpdateOrchardBlockRequest | Update block validation | Done
96 | User Profiles & Preferences | Form Requests | Form Request | StoreOrchardVarietyRequest | Add variety validation | Done
97 | User Profiles & Preferences | Form Requests | Form Request | UpdateOrchardVarietyRequest | Update variety validation | Done
98 | User Profiles & Preferences | Form Requests | Form Request | StoreOrchardActivityRequest | Create activity validation | Done
99 | User Profiles & Preferences | Form Requests | Form Request | UpdateOrchardActivityRequest | Update activity validation | Done
100 | User Profiles & Preferences | Form Requests | Form Request | StoreSprayLogRequest | Spray log validation | Done
User Profiles & Preferences
101 | User Profiles & Preferences | Policies | Policy | UserOrchardPolicy | Ownership & access control for orchards | Done
102 | User Profiles & Preferences | Policies | Policy | OrchardBlockPolicy | Block access control | Done
103 | User Profiles & Preferences | Policies | Policy | OrchardVarietyPolicy | Variety access control | Done
104 | User Profiles & Preferences | Policies | Policy | OrchardActivityPolicy | Activity access control | Done
Orchard Management
105 | Orchard Management | Database | Migration | spray_logs | Record of spray applications | Done
106 | Orchard Management | Database | Migration | disease_pressure_log | Observed disease severity per block | Done
107 | Orchard Management | Database | Migration | pest_tracker | Pest observation records | Done
108 | Orchard Management | Database | Migration | create_spray_logs | Spray log table creation | Done
Orchard Management
109 | Orchard Management | Models | Model | SprayLog | Spray application record | Done
110 | Orchard Management | Models | Model | DiseasePressureLog | Disease severity observation | Done
111 | Orchard Management | Models | Model | PestTracker | Pest observation & count | Done
Orchard Management
112 | Orchard Management | API Routes | API Route | GET/POST/PUT/DELETE /api/v1/orchards/{orchard}/disease-logs | Disease pressure log CRUD | Done
113 | Orchard Management | API Routes | API Route | GET/POST/PUT/DELETE /api/v1/orchards/{orchard}/pest-trackers | Pest tracker CRUD | Done
Orchard Management
114 | Orchard Management | Controllers | Controller | Api/DiseasePressureLogController | Disease log CRUD | Done
115 | Orchard Management | Controllers | Controller | Api/PestTrackerController | Pest tracker CRUD | Done
Spray Schedule
116 | Spray Schedule | Database | Migration | spray_fruits | Fruit types for spray calendar | Done
117 | Spray Schedule | Database | Migration | spray_regions | Geographic regions for spray timing | Done
118 | Spray Schedule | Database | Migration | spray_schedule_templates | Master spray schedule templates | Done
119 | Spray Schedule | Database | Migration | spray_schedule_stages | Individual spray stages within template | Done
120 | Spray Schedule | Database | Migration | spray_stage_disease_alerts | Disease alerts linked to stages | Done
121 | Spray Schedule | Database | Migration | spray_stage_chemical_recs | Chemical recommendations per stage | Done
122 | Spray Schedule | Database | Migration | spray_stage_tips | Farming tips per stage | Done
123 | Spray Schedule | Database | Migration | chemical_compat_rules | Chemical compatibility matrix | Done
124 | Spray Schedule | Database | Migration | nutrient_timing_rules | Nutrient application timing rules | Done
125 | Spray Schedule | Database | Migration | chemicals | Chemical/product database | Done
126 | Spray Schedule | Database | Migration | chemical_brands | Brand table for chemicals | Done
127 | Spray Schedule | Database | Migration | add_brands_to_chemicals | Brand linkage on chemicals | Done
128 | Spray Schedule | Database | Migration | make_chemical_descriptions_nullable | Schema tweak for chemicals | Done
Spray Schedule
129 | Spray Schedule | Models | Model | SprayFruit | Fruit type entity | Done
130 | Spray Schedule | Models | Model | SprayRegion | Geographic region entity | Done
131 | Spray Schedule | Models | Model | SprayScheduleTemplate | Master template | Done
132 | Spray Schedule | Models | Model | SprayScheduleStage | Individual stage | Done
133 | Spray Schedule | Models | Model | SprayStageDisease | Stage-disease alert pivot | Done
134 | Spray Schedule | Models | Model | SprayStageChemical | Stage-chemical recommendation pivot | Done
135 | Spray Schedule | Models | Model | SprayStageTip | Stage tip | Done
136 | Spray Schedule | Models | Model | ChemicalCompatRule | Compatibility rule | Done
137 | Spray Schedule | Models | Model | NutrientTimingRule | Nutrient timing rule | Done
138 | Spray Schedule | Models | Model | Chemical | Chemical/product | Done
139 | Spray Schedule | Models | Model | ChemicalBrand | Chemical brand | Done
Spray Schedule
140 | Spray Schedule | API Routes | API Route | GET /api/v1/spray-schedule | Full spray calendar for user | Done
141 | Spray Schedule | API Routes | API Route | GET /api/v1/spray-schedule/fruits | List spray fruits | Done
142 | Spray Schedule | API Routes | API Route | GET /api/v1/spray-schedule/compat-map | Chemical compatibility map | Done
143 | Spray Schedule | API Routes | API Route | POST /api/v1/shop/spray-schedule/task-done | Mark task complete | Done
144 | Spray Schedule | API Routes | API Route | POST /api/v1/shop/spray-schedule/save | Toggle save/follow schedule | Done
Spray Schedule
145 | Spray Schedule | Controllers | Controller | Api/SprayScheduleController | Spray schedule & task completion | Done
146 | Spray Schedule | Controllers | Controller | Admin/Spray* | Admin spray management (fruits, regions, templates, stages, compat, nutrient) | Done
Spray Schedule
147 | Spray Schedule | Services | Service | SprayScheduleService | Calendar logic, stage progression, task generation | Done
Disease Library & Prediction Engine
148 | Disease Library & Prediction Engine | Database | Migration | diseases | Disease/pest knowledge base | Done
149 | Disease Library & Prediction Engine | Database | Migration | disease_reports | Community disease reports | Done
150 | Disease Library & Prediction Engine | Database | Migration | pest_models | Pest phenology models | Done
151 | Disease Library & Prediction Engine | Database | Migration | pest_tracker | Pest observation tracking | Done
152 | Disease Library & Prediction Engine | Database | Migration | disease_pressure_log | Block-level disease pressure | Done
153 | Disease Library & Prediction Engine | Database | Migration | add_model_fields_to_diseases | Prediction model fields on diseases | Done
154 | Disease Library & Prediction Engine | Database | Migration | add_forecast_fields_to_weather | Forecast fields for predictions | Done
155 | Disease Library & Prediction Engine | Database | Migration | report_types | Community report categories | Done
156 | Disease Library & Prediction Engine | Database | Migration | add_report_fields_to_posts | Report metadata on posts | Done
157 | Disease Library & Prediction Engine | Database | Migration | make_posts_body_nullable | Allow report-only posts | Done
158 | Disease Library & Prediction Engine | Database | Migration | update_post_comments_to_polymorphic | Polymorphic comments for reports | Done
Disease Library & Prediction Engine
159 | Disease Library & Prediction Engine | Models | Model | Disease | Disease knowledge base entry | Done
160 | Disease Library & Prediction Engine | Models | Model | DiseaseReport | Community-submitted report | Done
161 | Disease Library & Prediction Engine | Models | Model | PestModel | Pest phenology model | Done
162 | Disease Library & Prediction Engine | Models | Model | PestTracker | Pest observation record | Done
163 | Disease Library & Prediction Engine | Models | Model | DiseasePressureLog | Observed pressure per block | Done
164 | Disease Library & Prediction Engine | Models | Model | ReportType | Report category type | Done
Disease Library & Prediction Engine
165 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/diseases | List diseases/pests | Done
166 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/diseases/{slug} | Disease detail | Done
167 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/predictions | Disease & pest predictions | Done
168 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/predictions/disease/{disease} | Specific disease prediction | Done
169 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/predictions/pest/{pestModel} | Specific pest prediction | Done
170 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/spray-window | Optimal spray window | Done
171 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/forecast/detailed | Detailed block forecast | Done
172 | Disease Library & Prediction Engine | API Routes | API Route | POST /api/v1/predictions/{log}/feedback | Farmer feedback on predictions | Done
173 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/blocks/{block}/predictions | Block-level predictions | Done
174 | Disease Library & Prediction Engine | API Routes | API Route | GET /api/v1/report-types | Available report types | Done
Disease Library & Prediction Engine
175 | Disease Library & Prediction Engine | Controllers | Controller | Api/DiseaseController | Disease library list/detail | Done
176 | Disease Library & Prediction Engine | Controllers | Controller | Api/PredictionController | All prediction endpoints | Done
177 | Disease Library & Prediction Engine | Controllers | Controller | Api/ReportTypeController | Report type list | Done
178 | Disease Library & Prediction Engine | Controllers | Controller | Admin/DiseaseController | Admin disease CRUD | Done
179 | Disease Library & Prediction Engine | Controllers | Controller | App/DiseaseReportController | Web disease report submission | Done
Disease Library & Prediction Engine
180 | Disease Library & Prediction Engine | Services | Service | Prediction/DiseasePressureService | Computes disease risk per orchard/block | Done
181 | Disease Library & Prediction Engine | Services | Service | Prediction/MicroclimateService | Microclimate analysis | Done
182 | Disease Library & Prediction Engine | Services | Service | Prediction/PestDevelopmentService | Pest degree-day tracking | Done
183 | Disease Library & Prediction Engine | Services | Service | Prediction/SprayWindowService | Evaluates spray windows | Done
184 | Disease Library & Prediction Engine | Services | Service | Prediction/Models/Pests/DegreeDayModel | Pest phenology model | Done
185 | Disease Library & Prediction Engine | Services | Service | Prediction/RecommendationGenerator | Spray recommendations generator | Done
186 | Disease Library & Prediction Engine | Services | Service | Prediction/LeafWetnessEstimator | Leaf wetness duration estimation | Done
187 | Disease Library & Prediction Engine | Services | Service | Disease/DiseaseReportService | Community report handling | Done
188 | Disease Library & Prediction Engine | Services | Service | Weather/DeltaTCalculator | Delta-T spray suitability | Done
Disease Library & Prediction Engine
189 | Disease Library & Prediction Engine | Jobs | Job | ComputePredictionsForUser | Background disease prediction computation | Done
190 | Disease Library & Prediction Engine | Jobs | Job | SendPredictionAlert | Queued prediction alert dispatch | Done
191 | Disease Library & Prediction Engine | Jobs | Job | NotifyNearbyUsersOfReport | Alert nearby users of critical disease reports | Done
Disease Library & Prediction Engine
192 | Disease Library & Prediction Engine | Form Requests | Form Request | PredictionFeedbackRequest | Feedback submission validation | Done
193 | Disease Library & Prediction Engine | Form Requests | Form Request | App/StoreDiseaseReportRequest | Disease report validation | Done
Disease Library & Prediction Engine
194 | Disease Library & Prediction Engine | Policies | Policy | DiseasePolicy | Disease CRUD authorization | Done
Weather Engine
195 | Weather Engine | Database | Migration | weather | Current weather & 7-day forecast storage | Done
196 | Weather Engine | Database | Migration | weather_alert_rules | User-configurable alert thresholds | Done
197 | Weather Engine | Database | Migration | add_forecast_fields_to_weather | Extended forecast fields | Done
198 | Weather Engine | Database | Migration | add_engine_fields_to_weather | Engine recommendation fields | Done
199 | Weather Engine | Database | Migration | weather_actuals | Observed vs forecast actuals | Done
200 | Weather Engine | Database | Migration | weather_engine_recommendations | Engine output storage | Done
201 | Weather Engine | Database | Migration | weather_forecast_archive | Historical forecast archive | Done
Weather Engine
202 | Weather Engine | Models | Model | Weather | Current conditions & forecast | Done
203 | Weather Engine | Models | Model | WeatherAlertRule | Alert threshold configuration | Done
204 | Weather Engine | Models | Model | WeatherActual | Observed weather data | Done
205 | Weather Engine | Models | Model | WeatherEngineRecommendation | Computed recommendations | Done
206 | Weather Engine | Models | Model | WeatherForecastArchive | Archived forecasts | Done
Weather Engine
207 | Weather Engine | API Routes | API Route | GET /api/v1/weather/current | Current weather for user's orchard | Done
208 | Weather Engine | API Routes | API Route | GET /api/v1/weather/alerts | Active weather alerts | Done
209 | Weather Engine | API Routes | API Route | GET /api/v1/weather/dashboard | Full weather dashboard data | Done
210 | Weather Engine | API Routes | API Route | GET /api/v1/weather/engine | Engine recommendations | Done
211 | Weather Engine | API Routes | API Route | GET /api/v1/weather/history | Historical weather data | Done
212 | Weather Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/fertigation-window | Fertigation timing recommendation | Done
213 | Weather Engine | API Routes | API Route | GET /api/v1/orchards/{orchard}/delta-t | Delta-T spray suitability | Done
Weather Engine
214 | Weather Engine | Controllers | Controller | Api/WeatherController | Current weather & alerts | Done
215 | Weather Engine | Controllers | Controller | Api/WeatherEngineController | Dashboard, engine, history, fertigation, delta-t | Done
216 | Weather Engine | Controllers | Controller | WeatherController | Web weather views | Done
217 | Weather Engine | Controllers | Controller | Admin/WeatherController | Admin weather data management | Done
218 | Weather Engine | Controllers | Controller | Admin/WeatherAlertRuleController | Alert rule CRUD | Done
Weather Engine
219 | Weather Engine | Services | Service | WeatherService | External weather API integration | Done
220 | Weather Engine | Services | Service | WeatherIntelligenceService | Weather data fetching & alerts | Done
221 | Weather Engine | Services | Service | Weather/WeatherEngine | Unified engine: spray/fertigation/disease recommendations | Done | TODO: integrate activity log for fertilizer
222 | Weather Engine | Services | Service | Weather/DeltaTCalculator | Delta-T calculation | Done
223 | Weather Engine | Services | Service | Weather/FertigationRecommender | Fertigation timing logic | Done
224 | Weather Engine | Services | Service | Weather/WeatherForecastArchiveService | Archive historical forecasts | Done
Weather Engine
225 | Weather Engine | Events & Listeners | Event | WeatherAlertTriggered | Alert threshold crossed | Done
226 | Weather Engine | Events & Listeners | Listener | SendWeatherAlertNotification | Dispatch weather alerts | Done
Blog / CMS
227 | Blog / CMS | Database | Migration | blog_categories | Blog category taxonomy | Done
228 | Blog / CMS | Database | Migration | blog_tags | Blog tag taxonomy | Done
229 | Blog / CMS | Database | Migration | blog_posts | Blog articles | Done
230 | Blog / CMS | Database | Migration | blog_post_tags | Post-tag pivot | Done
231 | Blog / CMS | Database | Migration | blog_post_related | Related post links | Done
232 | Blog / CMS | Database | Migration | blog_post_revisions | Content revision history | Done
233 | Blog / CMS | Database | Migration | blog_comments | Article comments | Done
234 | Blog / CMS | Database | Migration | media (Spatie) | Media library for images/docs | Done
Blog / CMS
235 | Blog / CMS | Models | Model | BlogCategory | Category entity | Done
236 | Blog / CMS | Models | Model | BlogTag | Tag entity | Done
237 | Blog / CMS | Models | Model | BlogPost | Article with revisions & SEO | Done
238 | Blog / CMS | Models | Model | BlogPostTag | Pivot | Done
239 | Blog / CMS | Models | Model | BlogPostRelated | Related linkage | Done
240 | Blog / CMS | Models | Model | BlogPostRevision | Revision snapshot | Done
241 | Blog / CMS | Models | Model | Comment | Comment/reply | Done
Blog / CMS
242 | Blog / CMS | API Routes | API Route | GET /api/v1/blog | List blog articles | Done
243 | Blog / CMS | API Routes | API Route | GET /api/v1/blog/{slug} | Article detail | Done
Blog / CMS
244 | Blog / CMS | Controllers | Controller | Api/BlogController | Public blog API | Done
245 | Blog / CMS | Controllers | Controller | Admin/BlogPostController | Admin blog CRUD | Done
246 | Blog / CMS | Controllers | Controller | Admin/BlogCategoryController | Category management | Done
247 | Blog / CMS | Controllers | Controller | Admin/BlogTagController | Tag management | Done
248 | Blog / CMS | Controllers | Controller | App/BlogController | Web blog views | Done
249 | Blog / CMS | Controllers | Controller | App/CommentController | Web comment management | Done
Blog / CMS
250 | Blog / CMS | Form Requests | Form Request | BlogPost/StoreBlogPostRequest | Create article validation | Done
251 | Blog / CMS | Form Requests | Form Request | BlogPost/UpdateBlogPostRequest | Update article validation | Done
Blog / CMS
252 | Blog / CMS | Policies | Policy | BlogPostPolicy | Article CRUD authorization | Done
Social / Community
253 | Social / Community | Database | Migration | posts | Social posts & Q&A | Done
254 | Social / Community | Database | Migration | post_comments | Comments & replies (polymorphic) | Done
255 | Social / Community | Database | Migration | likes | Post/comment likes | Done
256 | Social / Community | Database | Migration | post_templates | Post composer templates | Done
257 | Social / Community | Database | Migration | connections | User connections | Done
258 | Social / Community | Database | Migration | follows | User follows | Done
259 | Social / Community | Database | Migration | expert_profiles | Expert verification profiles | Done
260 | Social / Community | Database | Migration | expert_consultancy_charges | Expert fee structure | Done
261 | Social / Community | Database | Migration | messages | Direct messaging | Done
262 | Social / Community | Database | Migration | saved_content | Bookmarked posts/articles | Done
263 | Social / Community | Database | Migration | ratings | Expert/user ratings | Done
264 | Social / Community | Database | Migration | reputation_logs | Reputation score history | Done
265 | Social / Community | Database | Migration | post_helpful_marks | Mark comment as helpful | Done
266 | Social / Community | Database | Migration | stories | Instagram-style stories | Done
267 | Social / Community | Database | Migration | story_views | Story view tracking | Done
268 | Social / Community | Database | Migration | groups | Community groups | Done
269 | Social / Community | Database | Migration | group_members | Group membership | Done
270 | Social / Community | Database | Migration | group_join_requests | Group join requests | Done
271 | Social / Community | Database | Migration | group_rules | Group rules | Done
272 | Social / Community | Database | Migration | notifications | In-app notification storage | Done
Social / Community
273 | Social / Community | Models | Model | Post | Social post / Q&A / report | Done
274 | Social / Community | Models | Model | Comment | Comment & reply | Done
275 | Social / Community | Models | Model | Like | Like entity | Done
276 | Social / Community | Models | Model | PostTemplate | Composer template | Done
277 | Social / Community | Models | Model | Connection | Bi-directional user connection | Done
278 | Social / Community | Models | Model | Follow | One-way follow | Done
279 | Social / Community | Models | Model | ExpertProfile | Expert verification | Done
280 | Social / Community | Models | Model | ExpertConsultancyCharge | Expert pricing | Done
281 | Social / Community | Models | Model | Message | DM thread | Done
282 | Social / Community | Models | Model | SavedContent | Bookmark | Done
283 | Social / Community | Models | Model | Rating | Star rating | Done
284 | Social / Community | Models | Model | ReputationLog | Reputation event | Done
285 | Social / Community | Models | Model | HelpfulMark | Helpful mark on comment | Done
286 | Social / Community | Models | Model | Story | Ephemeral story | Done
287 | Social / Community | Models | Model | StoryView | Story view record | Done
288 | Social / Community | Models | Model | Group | Community group | Done
289 | Social / Community | Models | Model | GroupMember | Membership record | Done
290 | Social / Community | Models | Model | GroupJoinRequest | Pending join request | Done
291 | Social / Community | Models | Model | GroupRule | Group rule text | Done
292 | Social / Community | Models | Model | Notification | In-app notification | Done
Social / Community
293 | Social / Community | API Routes | API Route | GET /api/v1/feed | Personalized social feed | Done
294 | Social / Community | API Routes | API Route | GET /api/v1/questions | Q&A-only feed | Done
295 | Social / Community | API Routes | API Route | POST /api/v1/posts | Create post | Done
296 | Social / Community | API Routes | API Route | GET /api/v1/posts/{post} | Post detail | Done
297 | Social / Community | API Routes | API Route | DELETE /api/v1/posts/{post} | Delete post | Done
298 | Social / Community | API Routes | API Route | POST /api/v1/posts/{post}/like | Toggle like | Done
299 | Social / Community | API Routes | API Route | POST /api/v1/posts/{post}/share | Share post | Done
300 | Social / Community | API Routes | API Route | GET /api/v1/posts/{post}/comments | List comments | Done
301 | Social / Community | API Routes | API Route | POST /api/v1/posts/{post}/comments | Add comment | Done
302 | Social / Community | API Routes | API Route | POST /api/v1/comments/{comment}/reply | Reply to comment | Done
303 | Social / Community | API Routes | API Route | POST /api/v1/comments/{comment}/like | Like comment | Done
304 | Social / Community | API Routes | API Route | POST /api/v1/posts/{post}/comments/{comment}/helpful | Mark helpful | Done
305 | Social / Community | API Routes | API Route | DELETE /api/v1/posts/{post}/comments/{comment}/helpful | Unmark helpful | Done
306 | Social / Community | API Routes | API Route | GET /api/v1/post-templates | List composer templates | Done
307 | Social / Community | API Routes | API Route | GET /api/v1/stories/feed | Story feed | Done
308 | Social / Community | API Routes | API Route | GET /api/v1/stories/me | Own stories | Done
309 | Social / Community | API Routes | API Route | POST /api/v1/stories | Create story | Done
310 | Social / Community | API Routes | API Route | DELETE /api/v1/stories/{story} | Delete story | Done
311 | Social / Community | API Routes | API Route | POST /api/v1/stories/{story}/view | Mark story viewed | Done
312 | Social / Community | API Routes | API Route | GET /api/v1/stories/{story}/viewers | Story viewers list | Done
313 | Social / Community | API Routes | API Route | GET /api/v1/groups | List public groups | Done
314 | Social / Community | API Routes | API Route | GET /api/v1/groups/joined | List joined groups | Done
315 | Social / Community | API Routes | API Route | POST /api/v1/groups | Create group | Done
316 | Social / Community | API Routes | API Route | GET /api/v1/groups/{slug} | Group detail | Done
317 | Social / Community | API Routes | API Route | PUT /api/v1/groups/{slug} | Update group | Done
318 | Social / Community | API Routes | API Route | DELETE /api/v1/groups/{slug} | Delete group | Done
319 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/join | Join group | Done
320 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/leave | Leave group | Done
321 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/cancel-request | Cancel join request | Done
322 | Social / Community | API Routes | API Route | GET /api/v1/groups/{slug}/members | List members | Done
323 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/members/{user}/role | Update member role | Done
324 | Social / Community | API Routes | API Route | DELETE /api/v1/groups/{slug}/members/{user} | Remove member | Done
325 | Social / Community | API Routes | API Route | GET /api/v1/groups/{slug}/join-requests | Pending requests | Done
326 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/join-requests/{id}/approve | Approve request | Done
327 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/join-requests/{id}/reject | Reject request | Done
328 | Social / Community | API Routes | API Route | GET /api/v1/groups/{slug}/feed | Group post feed | Done
329 | Social / Community | API Routes | API Route | POST /api/v1/groups/{slug}/posts | Post in group | Done
330 | Social / Community | API Routes | API Route | DELETE /api/v1/groups/{slug}/posts/{post} | Delete group post | Done
331 | Social / Community | API Routes | API Route | GET /api/v1/notifications | Notification list | Done
332 | Social / Community | API Routes | API Route | GET /api/v1/notifications/unread-count | Unread count | Done
333 | Social / Community | API Routes | API Route | GET /api/v1/notifications/recent | Recent notifications | Done
334 | Social / Community | API Routes | API Route | GET /api/v1/notifications/{notification} | Notification detail | Done
335 | Social / Community | API Routes | API Route | POST /api/v1/notifications/{notification}/read | Mark as read | Done
336 | Social / Community | API Routes | API Route | POST /api/v1/notifications/read-all | Mark all read | Done
337 | Social / Community | API Routes | API Route | DELETE /api/v1/notifications/{notification} | Delete notification | Done
338 | Social / Community | API Routes | API Route | DELETE /api/v1/notifications/read | Delete all read notifications | Done
Social / Community
339 | Social / Community | Controllers | Controller | Api/PostController | Feed, posts, comments, likes, shares, questions | Done
340 | Social / Community | Controllers | Controller | Api/PostTemplateController | Composer templates | Done
341 | Social / Community | Controllers | Controller | Api/HelpfulMarkController | Helpful mark toggle | Done
342 | Social / Community | Controllers | Controller | Api/StoryController | Story CRUD & views | Done
343 | Social / Community | Controllers | Controller | Api/GroupController | Group CRUD | Done
344 | Social / Community | Controllers | Controller | Api/GroupMemberController | Membership & roles | Done
345 | Social / Community | Controllers | Controller | Api/GroupJoinRequestController | Join request management | Done
346 | Social / Community | Controllers | Controller | Api/GroupPostController | Group feed & posts | Done
347 | Social / Community | Controllers | Controller | Api/NotificationController | In-app notification CRUD | Done
348 | Social / Community | Controllers | Controller | Api/UserController | Suggested users, public profiles | Done
349 | Social / Community | Controllers | Controller | Admin/PostController | Admin post moderation | Done
350 | Social / Community | Controllers | Controller | Admin/CommentController | Comment moderation | Done
351 | Social / Community | Controllers | Controller | Admin/NotificationController | Admin notification dispatch | Done
Social / Community
352 | Social / Community | Services | Service | NotificationService | Push & DB notification dispatch | Done
353 | Social / Community | Services | Service | ActivityLogService | Audit logging | Done
Social / Community
354 | Social / Community | Jobs | Job | SendPushNotification | FCM push dispatch | Done
355 | Social / Community | Jobs | Job | SendDatabaseNotification | Queued DB notification insertion | Done
356 | Social / Community | Jobs | Job | IncrementViewCount | Deferred view counting | Done
Social / Community
357 | Social / Community | Events & Listeners | Event | ContentPublished | New post/article published | Done
358 | Social / Community | Events & Listeners | Event | DiseaseReportSubmitted | New disease report | Done
359 | Social / Community | Events & Listeners | Listener | SendContentPublishedNotification | Notify followers of new content | Done
360 | Social / Community | Events & Listeners | Listener | SendDiseaseReportNotification | Alert on disease reports | Done
361 | Social / Community | Events & Listeners | Listener | LogAuthenticationEvent | Audit auth events | Done
362 | Social / Community | Events & Listeners | Listener | NotifyAdminOfNewRegistration | Admin email on signup | Done
363 | Social / Community | Events & Listeners | Listener | SendWelcomeEmail | Welcome email on registration | Done
Social / Community
364 | Social / Community | API Resources | API Resource | PostResource | Post with like status & author | Done
365 | Social / Community | API Resources | API Resource | CommentResource | Comment with replies | Done
366 | Social / Community | API Resources | API Resource | NotificationResource | Notification payload | Done
367 | Social / Community | API Resources | API Resource | UserResource | Authenticated user with relations | Done
368 | Social / Community | API Resources | API Resource | PublicUserResource | Public profile data | Done
369 | Social / Community | API Resources | API Resource | UserProfileResource | Profile detail | Done
370 | Social / Community | API Resources | API Resource | PostTemplateResource | Template data | Done
371 | Social / Community | API Resources | API Resource | GroupCardResource | Group list card | Done
372 | Social / Community | API Resources | API Resource | GroupDetailResource | Group full detail | Done
373 | Social / Community | API Resources | API Resource | GroupMemberResource | Member list item | Done
eCommerce (Shop)
374 | eCommerce (Shop) | Database | Migration | brands | Product brands | Done
375 | eCommerce (Shop) | Database | Migration | categories | Product categories | Done
376 | eCommerce (Shop) | Database | Migration | products | Product catalog | Done
377 | eCommerce (Shop) | Database | Migration | product_attributes | Custom attribute definitions | Done
378 | eCommerce (Shop) | Database | Migration | product_attribute_values | Attribute value options | Done
379 | eCommerce (Shop) | Database | Migration | product_variants | SKU-level variants | Done
380 | eCommerce (Shop) | Database | Migration | product_variant_attribute_values | Variant-attribute pivot | Done
381 | eCommerce (Shop) | Database | Migration | product_reviews | Customer reviews | Done
382 | eCommerce (Shop) | Database | Migration | warehouses | Inventory locations | Done
383 | eCommerce (Shop) | Database | Migration | inventories | Stock levels per SKU/warehouse | Done
384 | eCommerce (Shop) | Database | Migration | stock_movements | Stock change audit trail | Done
385 | eCommerce (Shop) | Database | Migration | addresses | Customer shipping addresses | Done
386 | eCommerce (Shop) | Database | Migration | carts | Shopping cart | Done
387 | eCommerce (Shop) | Database | Migration | cart_items | Cart line items | Done
388 | eCommerce (Shop) | Database | Migration | wishlists | Wishlist items | Done
389 | eCommerce (Shop) | Database | Migration | coupons | Discount coupons | Done
390 | eCommerce (Shop) | Database | Migration | coupon_products | Coupon-product whitelist | Done
391 | eCommerce (Shop) | Database | Migration | coupon_categories | Coupon-category whitelist | Done
392 | eCommerce (Shop) | Database | Migration | coupon_usages | Coupon redemption history | Done
393 | eCommerce (Shop) | Database | Migration | orders | Customer orders | Done
394 | eCommerce (Shop) | Database | Migration | order_items | Order line items | Done
395 | eCommerce (Shop) | Database | Migration | order_status_histories | Order status audit trail | Done
396 | eCommerce (Shop) | Database | Migration | shipping_trackings | Shipment tracking | Done
397 | eCommerce (Shop) | Database | Migration | payments | Payment records | Done
398 | eCommerce (Shop) | Database | Migration | refunds | Refund records | Done
399 | eCommerce (Shop) | Database | Migration | invoices | Tax invoices | Done
400 | eCommerce (Shop) | Database | Migration | invoice_items | Invoice line items | Done
401 | eCommerce (Shop) | Database | Migration | add_fulltext_to_products | Fulltext search index | Done
402 | eCommerce (Shop) | Database | Migration | productables | Polymorphic product linkage | Done
403 | eCommerce (Shop) | Database | Migration | states | Indian states for addresses | Done
404 | eCommerce (Shop) | Database | Migration | districts | Districts for addresses | Done
eCommerce (Shop)
405 | eCommerce (Shop) | Models | Model | Shop/Brand | Product brand | Done
406 | eCommerce (Shop) | Models | Model | Shop/Category | Product category | Done
407 | eCommerce (Shop) | Models | Model | Shop/Product | Product with variants & attributes | Done
408 | eCommerce (Shop) | Models | Model | Shop/ProductAttribute | Attribute definition | Done
409 | eCommerce (Shop) | Models | Model | Shop/ProductAttributeValue | Attribute value | Done
410 | eCommerce (Shop) | Models | Model | Shop/ProductVariant | SKU variant | Done
411 | eCommerce (Shop) | Models | Model | Shop/ProductVariantAttributeValue | Variant attribute pivot | Done
412 | eCommerce (Shop) | Models | Model | Shop/ProductReview | Customer review | Done
413 | eCommerce (Shop) | Models | Model | Shop/Warehouse | Warehouse location | Done
414 | eCommerce (Shop) | Models | Model | Shop/Inventory | Stock level | Done
415 | eCommerce (Shop) | Models | Model | Shop/StockMovement | Stock movement audit | Done
416 | eCommerce (Shop) | Models | Model | Shop/Address | Shipping address | Done
417 | eCommerce (Shop) | Models | Model | Shop/Cart | Cart header | Done
418 | eCommerce (Shop) | Models | Model | Shop/CartItem | Cart line item | Done
419 | eCommerce (Shop) | Models | Model | Shop/Wishlist | Wishlist entry | Done
420 | eCommerce (Shop) | Models | Model | Shop/Coupon | Discount coupon | Done
421 | eCommerce (Shop) | Models | Model | Shop/CouponUsage | Redemption record | Done
422 | eCommerce (Shop) | Models | Model | Shop/Order | Customer order | Done
423 | eCommerce (Shop) | Models | Model | Shop/OrderItem | Order line item | Done
424 | eCommerce (Shop) | Models | Model | Shop/OrderStatusHistory | Status change log | Done
425 | eCommerce (Shop) | Models | Model | Shop/ShippingTracking | Shipment tracking | Done
426 | eCommerce (Shop) | Models | Model | Shop/Payment | Payment record | Done
427 | eCommerce (Shop) | Models | Model | Shop/Refund | Refund record | Done
428 | eCommerce (Shop) | Models | Model | Shop/Invoice | Tax invoice | Done
429 | eCommerce (Shop) | Models | Model | Shop/InvoiceItem | Invoice line item | Done
430 | eCommerce (Shop) | Models | Model | State | Indian state | Done
431 | eCommerce (Shop) | Models | Model | District | Indian district | Done
eCommerce (Shop)
432 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/categories | List categories | Done
433 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/categories/{slug} | Category detail | Done
434 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/brands | List brands | Done
435 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/brands/{slug} | Brand detail | Done
436 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/products | Product catalog with filters | Done
437 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/products/featured | Featured products | Done
438 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/products/{slug} | Product detail | Done
439 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/products/{slug}/reviews | Product reviews | Done
440 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/products/{slug}/reviews | Submit review | Done
441 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/products/{slug}/can-review | Eligibility check | Done
442 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/cart | View cart | Done
443 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/cart/items | Add to cart | Done
444 | eCommerce (Shop) | API Routes | API Route | PUT /api/v1/shop/cart/items/{itemId} | Update cart item | Done
445 | eCommerce (Shop) | API Routes | API Route | DELETE /api/v1/shop/cart/items/{itemId} | Remove cart item | Done
446 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/cart/coupon | Apply coupon | Done
447 | eCommerce (Shop) | API Routes | API Route | DELETE /api/v1/shop/cart/coupon | Remove coupon | Done
448 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/wishlist | View wishlist | Done
449 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/wishlist | Add to wishlist | Done
450 | eCommerce (Shop) | API Routes | API Route | DELETE /api/v1/shop/wishlist/{productId} | Remove from wishlist | Done
451 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/addresses | List addresses | Done
452 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/addresses | Create address | Done
453 | eCommerce (Shop) | API Routes | API Route | PUT /api/v1/shop/addresses/{id} | Update address | Done
454 | eCommerce (Shop) | API Routes | API Route | DELETE /api/v1/shop/addresses/{id} | Delete address | Done
455 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/addresses/{id}/default | Set default address | Done
456 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/checkout | Create order from cart | Done
457 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/orders | Order history | Done
458 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/shop/orders/{orderNumber} | Order detail | Done
459 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/shop/orders/{orderNumber}/cancel | Cancel order | Done
460 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/payments/razorpay/verify | Verify Razorpay payment | Done
461 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/payments/razorpay/order | Create Razorpay order | Done
462 | eCommerce (Shop) | API Routes | API Route | GET /api/v1/orders/{orderNumber}/invoice | Download invoice PDF | Done
463 | eCommerce (Shop) | API Routes | API Route | POST /api/v1/webhooks/razorpay | Razorpay webhook handler | Done
eCommerce (Shop)
464 | eCommerce (Shop) | Controllers | Controller | Api/Shop/CategoryController | Category API | Done
465 | eCommerce (Shop) | Controllers | Controller | Api/Shop/BrandController | Brand API | Done
466 | eCommerce (Shop) | Controllers | Controller | Api/Shop/ProductController | Product catalog API | Done
467 | eCommerce (Shop) | Controllers | Controller | Api/Shop/ProductReviewController | Reviews API | Done
468 | eCommerce (Shop) | Controllers | Controller | Api/Shop/CartController | Cart management | Done
469 | eCommerce (Shop) | Controllers | Controller | Api/Shop/WishlistController | Wishlist management | Done
470 | eCommerce (Shop) | Controllers | Controller | Api/Shop/AddressController | Address CRUD | Done
471 | eCommerce (Shop) | Controllers | Controller | Api/Shop/CheckoutController | Order creation | Done
472 | eCommerce (Shop) | Controllers | Controller | Api/Shop/OrderController | Order history & cancellation | Done
473 | eCommerce (Shop) | Controllers | Controller | Api/Shop/PaymentController | Razorpay integration | Done
474 | eCommerce (Shop) | Controllers | Controller | Api/Shop/InvoiceController | Invoice PDF download | Done
475 | eCommerce (Shop) | Controllers | Controller | Api/Shop/RazorpayWebhookController | Webhook handling | Done
476 | eCommerce (Shop) | Controllers | Controller | Web/Shop/* | Web shop views (cart, checkout, product, order) | Done
477 | eCommerce (Shop) | Controllers | Controller | Admin/Shop/* | Admin shop CRUD (brands, categories, products, attributes, warehouses, inventory, orders, payments, refunds, coupons, invoices, reports) | Done
eCommerce (Shop)
478 | eCommerce (Shop) | Services | Service | Shop/CartService | Add/update/remove items, coupon handling | Done | TODO: Validate coupon via CouponService in Phase 5
479 | eCommerce (Shop) | Services | Service | Shop/CheckoutService | Order creation, GST, addresses | Done
480 | eCommerce (Shop) | Services | Service | Shop/CouponService | Coupon validation & discount logic | Done
481 | eCommerce (Shop) | Services | Service | Shop/GstService | Indian GST calculation | Done
482 | eCommerce (Shop) | Services | Service | Shop/InventoryService | Stock reservation/commit/release | Done
483 | eCommerce (Shop) | Services | Service | Shop/InvoiceService | Invoice PDF generation (dompdf) | Done
484 | eCommerce (Shop) | Services | Service | Shop/OrderService | Order lifecycle, cancel, status | Done
485 | eCommerce (Shop) | Services | Service | Shop/PricingService | Price calculation with discounts | Done
486 | eCommerce (Shop) | Services | Service | Shop/ProductSearchService | Fulltext/catalog search | Done
487 | eCommerce (Shop) | Services | Service | Shop/RazorpayService | Razorpay order creation & verification | Done
Varieties & Rootstocks
488 | Varieties & Rootstocks | Database | Migration | varieties | Apple variety database | Done
489 | Varieties & Rootstocks | Database | Migration | rootstocks | Rootstock database | Done
Varieties & Rootstocks
490 | Varieties & Rootstocks | Models | Model | Variety | Apple variety with traits | Done
491 | Varieties & Rootstocks | Models | Model | Rootstock | Rootstock with characteristics | Done
Varieties & Rootstocks
492 | Varieties & Rootstocks | API Routes | API Route | GET /api/v1/varieties | List varieties | Done
493 | Varieties & Rootstocks | API Routes | API Route | GET /api/v1/varieties/{slug} | Variety detail | Done
494 | Varieties & Rootstocks | API Routes | API Route | GET /api/v1/rootstocks | List rootstocks | Done
495 | Varieties & Rootstocks | API Routes | API Route | GET /api/v1/rootstocks/{slug} | Rootstock detail | Done
Varieties & Rootstocks
496 | Varieties & Rootstocks | Controllers | Controller | Api/VarietyController | Variety API | Done
497 | Varieties & Rootstocks | Controllers | Controller | Api/RootstockController | Rootstock API | Done
498 | Varieties & Rootstocks | Controllers | Controller | Admin/VarietyController | Admin variety CRUD | Done
499 | Varieties & Rootstocks | Controllers | Controller | Admin/RootstockController | Admin rootstock CRUD | Done
500 | Varieties & Rootstocks | Controllers | Controller | App/VarietyController | Web variety views | Done
501 | Varieties & Rootstocks | Controllers | Controller | App/RootstockController | Web rootstock views | Done
Varieties & Rootstocks
502 | Varieties & Rootstocks | Form Requests | Form Request | Variety/StoreVarietyRequest | Create variety validation | Done
503 | Varieties & Rootstocks | Form Requests | Form Request | Variety/UpdateVarietyRequest | Update variety validation | Done
504 | Varieties & Rootstocks | Form Requests | Form Request | Rootstock/StoreRootstockRequest | Create rootstock validation | Done
505 | Varieties & Rootstocks | Form Requests | Form Request | Rootstock/UpdateRootstockRequest | Update rootstock validation | Done
Varieties & Rootstocks
506 | Varieties & Rootstocks | Policies | Policy | VarietyPolicy | Variety CRUD authorization | Done
507 | Varieties & Rootstocks | Policies | Policy | RootstockPolicy | Rootstock CRUD authorization | Done
Notifications
508 | Notifications | Database | Migration | notifications | In-app notification storage | Done
509 | Notifications | Database | Migration | device_tokens | FCM device token storage | Done
510 | Notifications | Database | Migration | add_notification_location_flags_to_user_preferences | Notification preference flags | Done
Notifications
511 | Notifications | Models | Model | Notification | In-app notification | Done
512 | Notifications | Models | Model | DeviceToken | Push token | Done
Notifications
513 | Notifications | Controllers | Controller | Api/NotificationController | In-app notification CRUD | Done
514 | Notifications | Controllers | Controller | Admin/NotificationController | Admin broadcast dispatch | Done
515 | Notifications | Controllers | Controller | NotificationController (Web) | Web notification views | Done
Notifications
516 | Notifications | Services | Service | NotificationService | Push & DB notification dispatch | Done
Notifications
517 | Notifications | Jobs | Job | SendPushNotification | FCM push dispatch | Done
518 | Notifications | Jobs | Job | SendDatabaseNotification | Queued DB insertion | Done
Admin Panel
519 | Admin Panel | Controllers | Controller | Admin/DashboardController | Admin dashboard | Done
520 | Admin Panel | Controllers | Controller | Admin/UserController | User management | Done
521 | Admin Panel | Controllers | Controller | Admin/RolePermissionController | RBAC management | Done
522 | Admin Panel | Controllers | Controller | Admin/ActivityLogController | Audit log viewer | Done
523 | Admin Panel | Controllers | Controller | Admin/MediaController | Media manager | Done
524 | Admin Panel | Controllers | Controller | Admin/SettingsController | Site settings | Done
525 | Admin Panel | Controllers | Controller | Admin/ReportTypeController | Report type CRUD | Done
526 | Admin Panel | Controllers | Controller | Admin/Shop/* | Shop admin (13 controllers) | Done
527 | Admin Panel | Controllers | Controller | Admin/Spray* | Spray schedule admin | Done
528 | Admin Panel | Controllers | Controller | Admin/Weather* | Weather admin | Done
529 | Admin Panel | Controllers | Controller | Admin/Blog* | Blog admin | Done
530 | Admin Panel | Controllers | Controller | Admin/DiseaseController | Disease admin | Done
531 | Admin Panel | Controllers | Controller | Admin/ChemicalController | Chemical admin | Done
532 | Admin Panel | Controllers | Controller | Admin/VarietyController | Variety admin | Done
533 | Admin Panel | Controllers | Controller | Admin/RootstockController | Rootstock admin | Done
Admin Panel
534 | Admin Panel | Views | View | admin/dashboard/ | Admin dashboard Blade | Done
535 | Admin Panel | Views | View | admin/users/ | User CRUD views | Done
536 | Admin Panel | Views | View | admin/roles/ | Role management views | Done
537 | Admin Panel | Views | View | admin/shop/ | Shop admin views (13 sub-modules) | Done
538 | Admin Panel | Views | View | admin/spray/ | Spray admin views | Done
539 | Admin Panel | Views | View | admin/weather/ | Weather admin views | Done
540 | Admin Panel | Views | View | admin/blog/ | Blog admin views | Done
541 | Admin Panel | Views | View | admin/diseases/ | Disease admin views | Done
542 | Admin Panel | Views | View | admin/chemicals/ | Chemical admin views | Done
543 | Admin Panel | Views | View | admin/varieties/ | Variety admin views | Done
544 | Admin Panel | Views | View | admin/rootstocks/ | Rootstock admin views | Done
545 | Admin Panel | Views | View | admin/media/ | Media manager views | Done
546 | Admin Panel | Views | View | admin/notifications/ | Notification broadcast views | Done
547 | Admin Panel | Views | View | admin/activity-logs/ | Audit log views | Done
548 | Admin Panel | Views | View | admin/comments/ | Comment moderation views | Done
549 | Admin Panel | Views | View | admin/posts/ | Post moderation views | Done
550 | Admin Panel | Views | View | admin/report_types/ | Report type views | Done
551 | Admin Panel | Views | View | admin/settings/ | Site settings views | Done
Web Frontend (PWA)
552 | Web Frontend (PWA) | Routes | Web Route | GET / | Home page | Done
553 | Web Frontend (PWA) | Routes | Web Route | GET /shop | Shop landing | Done
554 | Web Frontend (PWA) | Routes | Web Route | GET /blog | Blog landing | Done
555 | Web Frontend (PWA) | Routes | Web Route | GET /sitemap | XML sitemap | Done
556 | Web Frontend (PWA) | Routes | Web Route | GET /author/{slug} | Author page | Done
557 | Web Frontend (PWA) | Routes | Web Route | GET /newsletter | Newsletter signup | Done
558 | Web Frontend (PWA) | Routes | Web Route | GET /waitlist | Waitlist signup | Done
Web Frontend (PWA)
559 | Web Frontend (PWA) | Controllers | Controller | Web/HomeController | Public home | Done
560 | Web Frontend (PWA) | Controllers | Controller | Web/AboutController | About page | Done
561 | Web Frontend (PWA) | Controllers | Controller | Web/AuthorController | Author profile | Done
562 | Web Frontend (PWA) | Controllers | Controller | Web/NewsletterController | Newsletter subscription | Done
563 | Web Frontend (PWA) | Controllers | Controller | Web/SitemapController | SEO sitemap | Done
564 | Web Frontend (PWA) | Controllers | Controller | Web/WaitlistController | Waitlist signup | Done
565 | Web Frontend (PWA) | Controllers | Controller | App/* | Authenticated web app (dashboard, profile, orchards, spray, weather, etc.) | Done
Web Frontend (PWA)
566 | Web Frontend (PWA) | Views | View | app/home.blade.php | Authenticated dashboard | Done
567 | Web Frontend (PWA) | Views | View | app/profile.blade.php | User profile | Done
568 | Web Frontend (PWA) | Views | View | app/preferences.blade.php | User preferences | Done
569 | Web Frontend (PWA) | Views | View | app/orchards/ | Orchard management | Done
570 | Web Frontend (PWA) | Views | View | app/orchard-activities/ | Activity diary | Done
571 | Web Frontend (PWA) | Views | View | app/spray-schedule/ | Spray calendar | Done
572 | Web Frontend (PWA) | Views | View | app/weather/ | Weather forecast | Done
573 | Web Frontend (PWA) | Views | View | app/blog/ | Blog reader | Done
574 | Web Frontend (PWA) | Views | View | app/disease/ | Disease library | Done
575 | Web Frontend (PWA) | Views | View | app/variety/ | Variety browser | Done
576 | Web Frontend (PWA) | Views | View | app/rootstock/ | Rootstock browser | Done
577 | Web Frontend (PWA) | Views | View | app/chemical/ | Chemical database | Done
578 | Web Frontend (PWA) | Views | View | app/saved/ | Saved items | Done
579 | Web Frontend (PWA) | Views | View | app/comments/ | Comment management | Done
580 | Web Frontend (PWA) | Views | View | app/disease-reporter/ | Disease report submission | Done
581 | Web Frontend (PWA) | Views | View | app/notifications/ | Notification inbox | Done
Core Infrastructure
582 | Core Infrastructure | Config & Packages | Config | sanctum.php | API token config | Done
583 | Core Infrastructure | Config & Packages | Config | permission.php | Spatie RBAC config | Done
584 | Core Infrastructure | Config & Packages | Config | media-library.php | Spatie media config | Done
585 | Core Infrastructure | Config & Packages | Config | shop.php | Shop settings | Done
586 | Core Infrastructure | Config & Packages | Config | laravellocalization.php | Multi-language config | Done
587 | Core Infrastructure | Config & Packages | Package | laravel/framework ^12.0 | Core framework | Done
588 | Core Infrastructure | Config & Packages | Package | laravel/sanctum ^4.3 | API auth | Done
589 | Core Infrastructure | Config & Packages | Package | laravel/socialite ^5.27 | OAuth | Done
590 | Core Infrastructure | Config & Packages | Package | spatie/laravel-permission ^7.2 | RBAC | Done
591 | Core Infrastructure | Config & Packages | Package | spatie/laravel-medialibrary ^11.21 | Image uploads | Done
592 | Core Infrastructure | Config & Packages | Package | spatie/laravel-sitemap ^7.4 | SEO sitemaps | Done
593 | Core Infrastructure | Config & Packages | Package | spatie/laravel-sluggable ^3.8 | URL slugs | Done
594 | Core Infrastructure | Config & Packages | Package | razorpay/razorpay ^2.9 | Payments | Done
595 | Core Infrastructure | Config & Packages | Package | barryvdh/laravel-dompdf ^3.1 | Invoice PDFs | Done
596 | Core Infrastructure | Config & Packages | Package | kreait/laravel-firebase ^7.2 | FCM push | Done
597 | Core Infrastructure | Config & Packages | Package | artesaos/seotools ^1.3 | SEO meta | Done
598 | Core Infrastructure | Config & Packages | Package | mcamara/laravel-localization ^2.3 | Multi-language | Done
599 | Core Infrastructure | Config & Packages | Package | stevebauman/location ^7.6 | IP geolocation | Done
600 | Core Infrastructure | Config & Packages | Package | laravel/breeze ^2.3 | Auth scaffolding | Done
Core Infrastructure
601 | Core Infrastructure | Seeders & Factories | Seeder | DatabaseSeeder | Master seeder orchestrator | Done
602 | Core Infrastructure | Seeders & Factories | Seeder | UserSeeder | Sample users | Done
603 | Core Infrastructure | Seeders & Factories | Seeder | UserProfileSeeder | Sample profiles | Done
604 | Core Infrastructure | Seeders & Factories | Seeder | UserPreferenceSeeder | Sample preferences | Done
605 | Core Infrastructure | Seeders & Factories | Seeder | RoleAndPermissionSeeder | RBAC defaults | Done
606 | Core Infrastructure | Seeders & Factories | Seeder | VarietySeeder | Apple varieties | Done
607 | Core Infrastructure | Seeders & Factories | Seeder | RootstockSeeder | Rootstocks | Done
608 | Core Infrastructure | Seeders & Factories | Seeder | DiseaseSeeder | Diseases/pests | Done
609 | Core Infrastructure | Seeders & Factories | Seeder | DiseaseModelSeeder | Prediction models | Done
610 | Core Infrastructure | Seeders & Factories | Seeder | PestModelSeeder | Pest phenology models | Done
611 | Core Infrastructure | Seeders & Factories | Seeder | ChemicalSeeder | Chemicals & brands | Done
612 | Core Infrastructure | Seeders & Factories | Seeder | SprayScheduleSeeder | Spray templates & stages | Done
613 | Core Infrastructure | Seeders & Factories | Seeder | ShopSeeder | Shop catalog data | Done
614 | Core Infrastructure | Seeders & Factories | Seeder | BlogSeeder | Blog articles | Done
615 | Core Infrastructure | Seeders & Factories | Seeder | PostSeeder | Social posts | Done
616 | Core Infrastructure | Seeders & Factories | Seeder | PostTemplateSeeder | Composer templates | Done
617 | Core Infrastructure | Seeders & Factories | Seeder | GroupSeeder | Sample groups | Done
618 | Core Infrastructure | Seeders & Factories | Seeder | ConnectionSeeder | Sample connections | Done
619 | Core Infrastructure | Seeders & Factories | Seeder | FollowSeeder | Sample follows | Done
620 | Core Infrastructure | Seeders & Factories | Seeder | ExpertProfileSeeder | Expert profiles | Done
621 | Core Infrastructure | Seeders & Factories | Seeder | ExpertConsultancyChargeSeeder | Expert pricing | Done
622 | Core Infrastructure | Seeders & Factories | Seeder | OrchardVarietySeeder | Orchard variety mappings | Done
623 | Core Infrastructure | Seeders & Factories | Seeder | SprayLogSeeder | Sample spray logs | Done
624 | Core Infrastructure | Seeders & Factories | Seeder | UserOrchardSeeder | Sample orchards | Done
625 | Core Infrastructure | Seeders & Factories | Seeder | LocationSeeder | States & districts | Done
626 | Core Infrastructure | Seeders & Factories | Seeder | WeatherAlertRuleSeeder | Alert rule presets | Done
627 | Core Infrastructure | Seeders & Factories | Seeder | ReportTypeSeeder | Community report types | Done
628 | Core Infrastructure | Seeders & Factories | Factory | UserFactory | User factory | Done
629 | Core Infrastructure | Seeders & Factories | Factory | UserProfileFactory | Profile factory | Done
630 | Core Infrastructure | Seeders & Factories | Factory | UserPreferenceFactory | Preference factory | Done
631 | Core Infrastructure | Seeders & Factories | Factory | UserOrchardFactory | Orchard factory | Done
632 | Core Infrastructure | Seeders & Factories | Factory | VarietyFactory | Variety factory | Done
633 | Core Infrastructure | Seeders & Factories | Factory | RootstockFactory | Rootstock factory | Done
634 | Core Infrastructure | Seeders & Factories | Factory | DiseaseFactory | Disease factory | Done
635 | Core Infrastructure | Seeders & Factories | Factory | DiseaseReportFactory | Disease report factory | Done
636 | Core Infrastructure | Seeders & Factories | Factory | ChemicalFactory | Chemical factory | Done
637 | Core Infrastructure | Seeders & Factories | Factory | ChemicalBrandFactory | Chemical brand factory | Done
638 | Core Infrastructure | Seeders & Factories | Factory | BlogPostFactory | Blog article factory | Done
639 | Core Infrastructure | Seeders & Factories | Factory | BlogCategoryFactory | Blog category factory | Done
640 | Core Infrastructure | Seeders & Factories | Factory | BlogTagFactory | Blog tag factory | Done
641 | Core Infrastructure | Seeders & Factories | Factory | OrchardActivityFactory | Activity factory | Done
642 | Core Infrastructure | Seeders & Factories | Factory | NotificationFactory | Notification factory | Done

## Mobile (React Native)
S.No | Module / Feature | Sub-Module | Item Type | Item Name / File | Description | Status | Notes / TODOs
Auth & Onboarding
1 | Auth & Onboarding | Screens | Screen | LoginScreen.tsx | Multi-method auth: email/phone/password, OTP toggle, Google & Facebook social login, dev mock mode | Done
2 | Auth & Onboarding | Screens | Screen | EmailRegisterScreen.tsx | Email registration with name, village, district, state, language | Done
3 | Auth & Onboarding | Screens | Screen | PhoneAuthScreen.tsx | 2-step phone OTP flow (send → verify) | Done
4 | Auth & Onboarding | Screens | Screen | ForgotPasswordScreen.tsx | Password reset request | Done
5 | Auth & Onboarding | Screens | Screen | OnboardingScreen.tsx | Profile completion after first login | Done
6 | Auth & Onboarding | Screens | Screen | WelcomeScreen.tsx | 4-slide bilingual welcome carousel | Done
7 | Auth & Onboarding | Screens | Screen | NotificationPermissionScreen.tsx | FCM permission request | Done
8 | Auth & Onboarding | Screens | Screen | LocationPermissionScreen.tsx | GPS permission request | Done
Auth & Onboarding
9 | Auth & Onboarding | Components | Component | SocialAuthButtons.tsx | Google + Facebook login with dev mock fallback | Done
10 | Auth & Onboarding | Components | Component | AuthPromptBanner.tsx | Guest-user sign-in prompt | Done
Auth & Onboarding
11 | Auth & Onboarding | API Services | Service | authApi.ts | All auth endpoints: register, login, OTP, social, logout, profile, refresh, password | Done
12 | Auth & Onboarding | API Services | Service | socialAuth.ts | Google Sign-In & Facebook Login wrappers with dev mock | Done
Auth & Onboarding
13 | Auth & Onboarding | State Management | Store | authStore.ts | Zustand + MMKV: token, user, isAuthenticated, session restore | Done
14 | Auth & Onboarding | State Management | Store | onboardingStore.ts | Zustand + MMKV: onboarding & permission flags | Done
Home / Dashboard
15 | Home / Dashboard | Screens | Screen | HomeScreen.tsx | Segmented hub: Community (default) vs My Farm | Done
16 | Home / Dashboard | Screens | Screen | CommunitySegment.tsx | Full social feed with composer, Q&A, groups, likes, comments, shares | Done
17 | Home / Dashboard | Screens | Screen | MyFarmSegment.tsx | Compact farming dashboard — uses hard-coded mock data (API in Phase 6) | In Progress | Hard-coded data. Needs real API integration in Phase 6
18 | Home / Dashboard | Screens | Screen | CardDetailScreen.tsx | Generic priority card detail view | Done
19 | Home / Dashboard | Screens | Screen | FeedDetailScreen.tsx | Post detail with mock comments only (no live loading) | In Progress | Comments are mocked
20 | Home / Dashboard | Screens | Screen | PostDetailScreen.tsx | Live post detail: real post + comments, add comment, reply, like, helpful | Done
21 | Home / Dashboard | Screens | Screen | NotificationsScreen.tsx | In-app notification list with pull-to-refresh, infinite scroll, mark-as-read | Done
Home / Dashboard
22 | Home / Dashboard | Components | Component | dashboard/CompactHeroCard.tsx | Growth stage + weather hero | Done
23 | Home / Dashboard | Components | Component | dashboard/QuickStatsStrip.tsx | 4-stat horizontal strip | Done
24 | Home / Dashboard | Components | Component | dashboard/QuickActionsGrid.tsx | 4-action grid (log spray, weather, disease scan, tools) | Done
25 | Home / Dashboard | Components | Component | dashboard/CompactTaskList.tsx | Categorized task list | Done
26 | Home / Dashboard | Components | Component | dashboard/CompactForecastStrip.tsx | 7-day forecast scroll | Done
27 | Home / Dashboard | Components | Component | dashboard/HorizontalAlertStrip.tsx | Alerts/outbreaks scroll | Done
28 | Home / Dashboard | Components | Component | home/DoNowBanner.tsx | Priority action banner | Done
29 | Home / Dashboard | Components | Component | home/ForecastStrip.tsx | Forecast strip (old home) | Done
30 | Home / Dashboard | Components | Component | home/TopBlogs.tsx | Top blogs horizontal list | Done
31 | Home / Dashboard | Components | Component | home/TopContributors.tsx | Top contributors list | Done
32 | Home / Dashboard | Components | Component | home/TopRootstocks.tsx | Top rootstocks list | Done
33 | Home / Dashboard | Components | Component | home/TopVarieties.tsx | Top varieties list | Done
34 | Home / Dashboard | Components | Component | home/WeeklyTasks.tsx | Weekly tasks list | Done
35 | Home / Dashboard | Components | Component | home/AlertsSection.tsx | Alerts list (old home) | Done
36 | Home / Dashboard | Components | Component | SegmentedControl.tsx | Bilingual segmented tabs | Done
37 | Home / Dashboard | Components | Component | SectionHeader.tsx | Section title with See All | Done
38 | Home / Dashboard | Components | Component | StoryComposer.tsx | Story creation trigger | Done
39 | Home / Dashboard | Components | Component | ReportComposerSheet.tsx | Community event report composer | Done
40 | Home / Dashboard | Components | Component | PostImages.tsx | Post image grid (1-4) | Done
41 | Home / Dashboard | Components | Component | ShareSheet.tsx | WhatsApp/Copy/Native share bottom sheet | Done
Home / Dashboard
42 | Home / Dashboard | API Services | Service | postApi.ts | Feed, posts, comments, likes, shares, questions, helpful marks | Done
43 | Home / Dashboard | API Services | Service | storyApi.ts | Stories feed, create, view, viewers, delete | Done
44 | Home / Dashboard | API Services | Service | userApi.ts | Suggested users, public profile | Done
45 | Home / Dashboard | API Services | Service | profileApi.ts | Own posts, liked posts, activities, stats | Done
46 | Home / Dashboard | API Services | Service | reportApi.ts | Report types, create report post | Done
47 | Home / Dashboard | API Services | Service | notificationService.ts | FCM: permission, token, register, deep-link mapping | Done
48 | Home / Dashboard | API Services | Service | api/notifications.ts | In-app notification API wrapper | Done
Home / Dashboard
49 | Home / Dashboard | State Management | Store | notificationStore.ts | Zustand: notifications array, unreadCount, pagination | Done
50 | Home / Dashboard | State Management | Store | toastStore.ts | Zustand: toast visibility, message, type, duration | Done
Home / Dashboard
51 | Home / Dashboard | Hooks | Hook | useNotifications.ts | Infinite scroll notifications, mark read, delete | Done
Orchard Management
52 | Orchard Management | Screens | Screen | OrchardListScreen.tsx | List user's orchards with CRUD | Done
53 | Orchard Management | Screens | Screen | OrchardFormScreen.tsx | Create/edit orchard: location, GPS, altitude, area, farming type, irrigation | Done
54 | Orchard Management | Screens | Screen | OrchardDetailScreen.tsx | Orchard detail with blocks, varieties, spray logs, disease logs | Done
55 | Orchard Management | Screens | Screen | BlockFormScreen.tsx | Create/edit block: area, soil, aspect, frost risk, variety-rootstock | Done
56 | Orchard Management | Screens | Screen | OrchardVarietyFormScreen.tsx | Add/edit varieties to orchard (bulk add) | Done
Orchard Management
57 | Orchard Management | API Services | Service | orchardApi.ts | Orchard CRUD, Block CRUD, Variety CRUD, Spray Logs, Disease Logs, Pest Trackers | Done
Orchard Management
58 | Orchard Management | State Management | Store | orchardStore.ts | Zustand + MMKV: orchards list, selectedOrchardId | Done
Orchard Management
59 | Orchard Management | Hooks | Hook | useOrchards.ts | Fetch orchards list, refresh, delete | Done
60 | Orchard Management | Hooks | Hook | useOrchardDetail.ts | Fetch orchard detail by ID | Done
Spray Schedule
61 | Spray Schedule | Screens | Screen | SprayScreen.tsx | Full spray calendar: fruit/region selector, stage tracker, fungicide/insecticide tabs, tank-size dosage, disease alerts, tips, task completion, WhatsApp share | Done
Spray Schedule
62 | Spray Schedule | API Services | Service | sprayApi.ts | Spray schedule, fruits, compat-map, task-done, save toggle | Done
Spray Schedule
63 | Spray Schedule | Hooks | Hook | useSpraySchedule.ts | Fetch schedule, mark task done, toggle watch, tank size | Done
Knowledge / Discover
64 | Knowledge / Discover | Screens | Screen | DiscoverScreen.tsx | Knowledge hub. Top half mock dashboard (Do Now, weather, tasks, alerts). Bottom half real navigation | In Progress | Dashboard mocked. Needs real API data
65 | Knowledge / Discover | Screens | Screen | VarietyScreen.tsx | Variety list with season & altitude filters, compare mode (up to 3) | Done
66 | Knowledge / Discover | Screens | Screen | VarietyDetailScreen.tsx | Full variety detail: tree/fruit/harvest/climate/disease/market | Done
67 | Knowledge / Discover | Screens | Screen | VarietyCompareScreen.tsx | Side-by-side comparison table | Done
68 | Knowledge / Discover | Screens | Screen | DiseaseScreen.tsx | Disease/pest library with severity & category filters | Done
69 | Knowledge / Discover | Screens | Screen | DiseaseDetailScreen.tsx | Disease detail: identification, prevention, organic treatment, yield loss | Done
70 | Knowledge / Discover | Screens | Screen | RootstockListScreen.tsx | Rootstock list with vigour filters | Done
71 | Knowledge / Discover | Screens | Screen | RootstockDetailScreen.tsx | Rootstock detail: planting, resistance, soil | Done
72 | Knowledge / Discover | Screens | Screen | BlogScreen.tsx / BlogListScreen.tsx | Blog list with category filters, featured section | Done
73 | Knowledge / Discover | Screens | Screen | BlogDetailScreen.tsx | Article view with hero image, bilingual toggle, related articles | Done
74 | Knowledge / Discover | Screens | Screen | WeatherScreen.tsx | Real weather dashboard: current, spray/fertigation recs, 7-day forecast, 30-day trends, alerts | Done
75 | Knowledge / Discover | Screens | Screen | ToolsScreen.tsx | Kisan Tools hub: 26 calculator widgets grid. All show 'Coming soon' on tap | In Progress | UI catalog complete. 26 calculator widgets pending implementation
Knowledge / Discover
76 | Knowledge / Discover | Components | Component | VarietyCard.tsx | Variety list card with compare toggle | Done
Knowledge / Discover
77 | Knowledge / Discover | API Services | Service | varietyApi.ts | Varieties list & detail | Done
78 | Knowledge / Discover | API Services | Service | diseaseApi.ts | Diseases list & detail | Done
79 | Knowledge / Discover | API Services | Service | rootstockApi.ts | Rootstocks list & detail | Done
80 | Knowledge / Discover | API Services | Service | blogApi.ts | Blog list & detail | Done
81 | Knowledge / Discover | API Services | Service | weatherApi.ts | Current, alerts, dashboard, engine, history, fertigation, delta-t | Done
Knowledge / Discover
82 | Knowledge / Discover | Hooks | Hook | useVarieties.ts | Fetch varieties with filters, pagination, compare | Done
83 | Knowledge / Discover | Hooks | Hook | useVarietyDetail.ts | Fetch variety by slug | Done
84 | Knowledge / Discover | Hooks | Hook | useDiseases.ts | Fetch diseases with filters, pagination | Done
85 | Knowledge / Discover | Hooks | Hook | useDiseaseDetail.ts | Fetch disease by slug | Done
86 | Knowledge / Discover | Hooks | Hook | useRootstocks.ts | Fetch rootstocks with filters | Done
87 | Knowledge / Discover | Hooks | Hook | useRootstockDetail.ts | Fetch rootstock by slug | Done
88 | Knowledge / Discover | Hooks | Hook | useBlogs.ts | Fetch blog list with filters, pagination, featured | Done
89 | Knowledge / Discover | Hooks | Hook | useBlogDetail.ts | Fetch single blog by slug | Done
Shop / eCommerce
90 | Shop / eCommerce | Screens | Screen | ShopScreen.tsx | Shop hub: search, category grid, featured products | Done
91 | Shop / eCommerce | Screens | Screen | ProductListScreen.tsx | Product listing with filters, sorting, pagination | Done
92 | Shop / eCommerce | Screens | Screen | ProductDetailScreen.tsx | Product detail: gallery, variants, reviews, add-to-cart, wishlist | Done
93 | Shop / eCommerce | Screens | Screen | CartScreen.tsx | Cart items, quantity update, remove, subtotal, checkout | Done
94 | Shop / eCommerce | Screens | Screen | CheckoutScreen.tsx | Razorpay payment: select address, create order, Razorpay SDK, verify | Done
95 | Shop / eCommerce | Screens | Screen | AddressListScreen.tsx | Manage shipping addresses | Done
96 | Shop / eCommerce | Screens | Screen | AddEditAddressScreen.tsx | Create/edit address with state/district dropdowns | Done
97 | Shop / eCommerce | Screens | Screen | OrderListScreen.tsx | Order history with status badges | Done
98 | Shop / eCommerce | Screens | Screen | OrderDetailScreen.tsx | Order detail with timeline, items, tracking | Done
Shop / eCommerce
99 | Shop / eCommerce | Components | Component | shop/ProductCard.tsx | Product list card with image, rating, price | Done
100 | Shop / eCommerce | Components | Component | shop/CategoryCard.tsx | Category card with icon and color | Done
101 | Shop / eCommerce | Components | Component | shop/PriceTag.tsx | Price with compare-at and discount badge | Done
102 | Shop / eCommerce | Components | Component | shop/QuantitySelector.tsx | +/- quantity stepper | Done
103 | Shop / eCommerce | Components | Component | shop/StarRating.tsx | Star rating display | Done
Shop / eCommerce
104 | Shop / eCommerce | API Services | Service | shopApi.ts | Categories, brands, products, cart, wishlist, addresses, checkout, Razorpay, orders, reviews | Done
Shop / eCommerce
105 | Shop / eCommerce | State Management | Store | cartStore.ts | Zustand + MMKV: cart items, counts, totals, coupon. Syncs with backend | Done
Shop / eCommerce
106 | Shop / eCommerce | Hooks | Hook | useProducts.ts | Fetch products with filters, sorting, pagination, featured | Done
107 | Shop / eCommerce | Hooks | Hook | useProductDetail.ts | Fetch product by slug | Done
108 | Shop / eCommerce | Hooks | Hook | useCart.ts | Auto-load cart on auth change | Done
109 | Shop / eCommerce | Hooks | Hook | useOrders.ts | Fetch orders with pagination | Done
110 | Shop / eCommerce | Hooks | Hook | useAddresses.ts | Fetch addresses list | Done
Community / Social
111 | Community / Social | Screens | Screen | CommunityScreen.tsx | Q&A feed: questions only, like, infinite scroll | Done
112 | Community / Social | Screens | Screen | GroupListScreen.tsx | Discover public/private groups | Done
113 | Community / Social | Screens | Screen | GroupDetailScreen.tsx | Group detail: cover, rules, join/leave, member list, feed | Done
114 | Community / Social | Screens | Screen | GroupCreateScreen.tsx | Create group with name, description, visibility, cover/avatar, rules | Done
115 | Community / Social | Screens | Screen | GroupEditScreen.tsx | Edit group | Done
116 | Community / Social | Screens | Screen | GroupJoinRequestsScreen.tsx | Approve/reject pending join requests | Done
117 | Community / Social | Screens | Screen | MyGroupsScreen.tsx | List joined groups | Done
118 | Community / Social | Screens | Screen | UserProfileScreen.tsx | Public profile: orchards, expert charges, follow/connect buttons | In Progress | Follow/Connect buttons show 'coming soon' toast
119 | Community / Social | Screens | Screen | MyProfileScreen.tsx | Own profile: Posts, Activities, Likes tabs, stats header | Done
120 | Community / Social | Screens | Screen | EditProfileScreen.tsx | Edit name, email, phone, village, district, state, language | Done
121 | Community / Social | Screens | Screen | ProfileScreen.tsx | My Orchard tab root: profile card, orchard list, groups, settings, logout | Done
Community / Social
122 | Community / Social | API Services | Service | groupApi.ts | Groups CRUD, join/leave, members, roles, join requests, group feed/posts | Done
Community / Social
123 | Community / Social | Hooks | Hook | useCurrentLocation.ts | GPS permission + geolocation + Nominatim reverse geocoding | Done
124 | Community / Social | Hooks | Hook | useLocations.ts | Fetch states/districts for forms | Done
Stories
125 | Stories | Screens | Screen | StoryViewerScreen.tsx | Instagram-style story viewer: swipe, tap, long-press, progress bars, video, viewers modal | Done
126 | Stories | Screens | Screen | StoryTextComposer.tsx | Create text story with colored background picker | Done
127 | Stories | Screens | Screen | StoryMediaPreview.tsx | Preview image/video before posting as story | Done
Navigation
128 | Navigation | Navigation Files | Navigation | AppNavigator.tsx | Root navigator: auth gating, FCM init, token refresh, deep-link handling | Done
129 | Navigation | Navigation Files | Navigation | BottomTabNavigator.tsx | 5-tab bar: Home, Spray, Shop (FAB), Discover, MyOrchard | Done
130 | Navigation | Navigation Files | Navigation | CustomTabBar.tsx | LeafSnap-style compact tab bar with center Shop FAB | Done
131 | Navigation | Navigation Files | Navigation | AuthStack.tsx | Login, EmailRegister, PhoneAuth, ForgotPassword, Onboarding | Done
132 | Navigation | Navigation Files | Navigation | OnboardingStack.tsx | Welcome, NotificationPermission, LocationPermission | Done
133 | Navigation | Navigation Files | Navigation | stacks/HomeStack.tsx | 20+ screens: Home, PostDetail, UserProfile, GroupDetail, Variety, Disease, Weather, Blog, StoryViewer, Tools, etc. | Done
134 | Navigation | Navigation Files | Navigation | stacks/ShopStack.tsx | Shop, ProductList, ProductDetail, Cart, Checkout, AddressList, AddEditAddress, OrderList, OrderDetail | Done
135 | Navigation | Navigation Files | Navigation | stacks/DiscoverStack.tsx | Discover, Tools, Variety, Disease, Weather, Blog, Rootstock, GroupList | Done
136 | Navigation | Navigation Files | Navigation | stacks/MyOrchardStack.tsx | Profile, MyProfile, EditProfile, MyGroups, OrchardList, OrchardDetail, OrchardForm, BlockForm, VarietyForm | Done
137 | Navigation | Navigation Files | Navigation | stacks/CommunityStack.tsx | Community, PostDetail, ImageViewer, UserProfile | Done
138 | Navigation | Navigation Files | Navigation | stacks/SprayStack.tsx | Spray calendar only | Done
139 | Navigation | Navigation Files | Navigation | navigationRef.ts | Navigation ref for external navigation + navigateToLogin helper | Done
140 | Navigation | Navigation Files | Navigation | types.ts | TypeScript types for all stack param lists | Done
UI Components
141 | UI Components | Generic Components | Component | ScreenLayout.tsx | Global wrapper: scroll, safe padding, pull-to-refresh, dynamic header compaction | Done
142 | UI Components | Generic Components | Component | ScreenWrapper.tsx | Simple safe-area wrapper | Done
143 | UI Components | Generic Components | Component | GlobalHeader.tsx | Orchard-aware header with weather, notifications bell, avatar | Done
144 | UI Components | Generic Components | Component | AppHeader.tsx | Alternative header | Done
145 | UI Components | Generic Components | Component | Toast.tsx | Global toast (Android-style dark pill) | Done
146 | UI Components | Generic Components | Component | Skeleton.tsx | Shimmer loading placeholder | Done
147 | UI Components | Generic Components | Component | EmptyState.tsx | Bilingual empty state with icon | Done
148 | UI Components | Generic Components | Component | SmartImage.tsx | FastImage wrapper with skeleton & fallback | Done
149 | UI Components | Generic Components | Component | PressableScale.tsx | TouchableOpacity with spring scale | Done
150 | UI Components | Generic Components | Component | ModernCard.tsx | Generic modern card | Done
151 | UI Components | Generic Components | Component | FormDropdown.tsx | Custom dropdown picker | Done
152 | UI Components | Generic Components | Component | ImageViewerScreen.tsx | Full-screen image pager with counter | Done
Theme / Styling
153 | Theme / Styling | Theme Files | Theme | theme/colors.ts | Core palette, semantic colors, surface colors, priority helpers | Done
154 | Theme / Styling | Theme Files | Theme | theme/style.ts | Spacing tokens (8px grid), radius, shadows, global StyleSheet | Done
155 | Theme / Styling | Theme Files | Theme | theme/animations.ts | Duration, easing, spring presets, animateTo, pressScale, fadeInUp, staggerDelay | Done
Theme / Styling
156 | Theme / Styling | Typography | Typography | typography/fonts.ts | Inter & Noto Sans Devanagari | Done
157 | Theme / Styling | Typography | Typography | typography/sizes.ts | Font size scale | Done
158 | Theme / Styling | Typography | Typography | typography/weights.ts | Font weight scale | Done
159 | Theme / Styling | Typography | Typography | typography/lineHeights.ts | Line height scale | Done
160 | Theme / Styling | Typography | Typography | typography/styles.ts | 100+ predefined text styles | Done
161 | Theme / Styling | Typography | Typography | typography/Typography.tsx | Master Typography component with variant prop | Done
162 | Theme / Styling | Typography | Typography | typography/PrimaryHeading.tsx | Pre-configured heading | Done
163 | Theme / Styling | Typography | Typography | typography/HindiText.tsx | Hindi text wrapper | Done
164 | Theme / Styling | Typography | Typography | typography/SectionHeader.tsx | Section title | Done
165 | Theme / Styling | Typography | Typography | typography/CardTitle.tsx | Card title | Done
166 | Theme / Styling | Typography | Typography | typography/MetaText.tsx | Meta/caption text | Done
167 | Theme / Styling | Typography | Typography | typography/BadgeText.tsx | Badge label | Done
168 | Theme / Styling | Typography | Typography | typography/NavLabel.tsx | Navigation label | Done
169 | Theme / Styling | Typography | Typography | typography/StatText.tsx | Stat number | Done
Types & Config
170 | Types & Config | Types | Type | types/index.ts | GrowthStage, Brand, TaskItem, DiseaseWatchItem, SoilNutritionItem, WeatherWarning, PreventiveAlert, OutbreakAlert, Variety, Rootstock, BlogPost, Contributor, ForecastDay, NavItem, Orchard, HeaderWeather, HomeScreenData, PriorityMeta, ApiResponse<T>, NotificationItem, NotificationsResponse, UnreadCountResponse | Done
171 | Types & Config | Types | Type | types/razorpay.d.ts | react-native-razorpay type declarations | Done
Types & Config
172 | Types & Config | Config | Config | config/env.ts | API_BASE_URL, GOOGLE_WEB_CLIENT_ID, FACEBOOK_APP_ID, RAZORPAY_KEY_ID | Done
173 | Types & Config | Config | Config | config/socialAuth.ts | Social auth config with dev mock toggle | Done
Native Modules / Permissions
174 | Native Modules / Permissions | Modules | Native Module | @react-native-firebase/messaging | Push notifications, token lifecycle, deep links | Done
175 | Native Modules / Permissions | Modules | Native Module | @react-native-google-signin/google-signin | Google OAuth | Done
176 | Native Modules / Permissions | Modules | Native Module | react-native-fbsdk-next | Facebook Login | Done
177 | Native Modules / Permissions | Modules | Native Module | react-native-razorpay | Payment checkout | Done
178 | Native Modules / Permissions | Modules | Native Module | react-native-fast-image | Cached images | Done
179 | Native Modules / Permissions | Modules | Native Module | react-native-vector-icons/MaterialCommunityIcons | All icons | Done
180 | Native Modules / Permissions | Modules | Native Module | react-native-image-picker | Camera & gallery | Done
181 | Native Modules / Permissions | Modules | Native Module | react-native-video | Story video playback | Done
182 | Native Modules / Permissions | Modules | Native Module | react-native-permissions | Location, notification, camera, storage | Done
183 | Native Modules / Permissions | Modules | Native Module | @react-native-community/geolocation | GPS coordinates | Done
184 | Native Modules / Permissions | Modules | Native Module | react-native-safe-area-context | Safe area insets | Done
185 | Native Modules / Permissions | Modules | Native Module | react-native-mmkv | Encrypted local storage | Done
186 | Native Modules / Permissions | Modules | Native Module | axios | HTTP client with interceptors | Done